## Sheet1
Change Request Number | Change Type | Change Description | Change Priority | Status | Group Assigned | Action to Complete | Date Modified | End Date
CR-001 | Feature Addition | Integration of a RESTful API for seamless interaction with third-party payment gateways and financial institutions is underway. This involves collaboration with API providers to establish secure communication channels and implement API endpoints according to technical specifications. | Medium | Open | Development | Collaborate closely with API providers to define requirements, establish secure communication channels, and develop API endpoints. Ensure compatibility and reliability of API integrations through thorough testing and validation procedures. | 2024-03-21 | 2024-04-15
CR-002 | Stakeholder | A team member substitution is underway to address resource allocation issues and ensure project continuity. This involves identifying a replacement candidate and conducting necessary onboarding procedures for a smooth transition. | High | Open | Project Team | Identify suitable candidates for the position and conduct interviews to select the replacement team member. Develop an onboarding plan to facilitate a smooth transition and ensure continuity of project activities. | 2024-03-21 | 2024-03-25
CR-003 | Design Update | User interface design is being revised to enhance accessibility and cross-browser compatibility. This includes conducting performance testing across different devices and browsers to optimize user experience and ensure consistent rendering of UI components. | High | Open | Design Team | Conduct usability testing sessions with target users to gather feedback on the revised UI design. Iterate based on user insights and preferences to optimize accessibility and cross-browser compatibility. Ensure seamless rendering across various devices and browsers. | 2024-03-21 | 2024-04-30
CR-004 | Scope Adjustment | The project scope is expanding to include broader functionality such as multi-factor authentication and data encryption for enhanced security measures. This necessitates a comprehensive feasibility study to assess implementation complexity and resource requirements. | High | Open | Project Team | Conduct a detailed feasibility study to evaluate the technical complexity and resource implications of integrating advanced security features. Identify potential challenges and develop strategies to address them effectively. | 2024-03-21 | 2024-04-05
CR-005 | Communication | Regular meetings between developers and analysts are scheduled to facilitate collaboration on technical requirements and system architecture discussions. This involves establishing a recurring meeting schedule and agenda to ensure productive discussions and decision-making. | High | Pending | Project Team | Set up recurring meetings between developers and analysts to discuss technical requirements and system architecture. Develop a structured agenda to guide discussions and ensure alignment with project objectives. Foster collaboration and knowledge sharing among team members. | 2024-03-21 | 2024-04-01
CR-006 | Feature Addition | A monthly report download to email option is being implemented for end users within the application to facilitate data access and analysis. This requires development of functionality to generate and send monthly reports via email, ensuring compatibility and user-friendly interface. | Medium | Open | Development | Develop functionality to generate and send monthly reports via email. Ensure seamless integration with existing system architecture and user-friendly interface design. Conduct thorough testing to validate functionality and performance | 2024-03-21 | 2024-04-10
CR-007 | Bug Fix | Addressing the issue where failed payments are not being updated within the system to ensure accurate payment status tracking. This involves investigating the root cause of the issue and implementing necessary fixes. | High | Open | Development | Investigate the root cause of payment update failures and develop a plan to address the issue. Implement necessary fixes and conduct thorough testing to ensure proper functionality and data accuracy. | 2024-03-21 | 2024-04-05
CR-008 | Design Update | The color scheme for the application's home screen logo is being updated to red and white for improved visual appeal and brand consistency. This requires a review of current design guidelines and implementation of color changes according to brand standards. | Medium | Open | Design Team | Review current design guidelines and implement the color changes according to brand standards. Ensure consistency with brand identity and visual aesthetics. Conduct user testing to gather feedback on the updated color scheme. | 2024-03-21 | 2024-03-31
CR-009 | Design Update | Client' is being replaced with 'customer' throughout the webpage for consistency in terminology and user experience. This involves conducting a thorough review of webpage content and updating all instances of 'client' to 'customer' accordingly. | Low | Open | Design Team | Conduct a comprehensive review of webpage content and update all instances of 'client' to 'customer' terminology. Ensure consistency and clarity in communication across the platform. | 2024-03-21 | 2024-04-05
CR-010 | Security Update | Enhanced security protocols, such as tokenization and role-based access control, are being implemented to bolster data protection mechanisms within the application. This involves thorough penetration testing, code reviews, and compliance validation to ensure adherence to industry standards and regulatory requirements. | High | Pending | Security Team | Execute extensive security testing procedures, including penetration testing and code reviews, to validate the effectiveness of the implemented security measures. Ensure compliance with industry standards and regulatory mandates. | 2024-03-21 | 2024-04-10
CR-011 | Stakeholder | The Legal Compliance team has been added as a stakeholder to address regulatory requirements and ensure legal adherence throughout the project lifecycle. This entails scheduling detailed meetings and technical briefings to discuss compliance needs and integrate necessary controls into the application architecture. | Medium | Open | Project Team | Organize meetings with Legal Compliance representatives to discuss regulatory requirements and incorporate necessary controls into the application design and development process. Ensure alignment with legal standards and regulatory mandates. | 2024-03-21 | 2024-04-02